{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":15,"n_cols":8,"rows_kept":15,"merged":[[0,0,0,7],[1,1,1,2],[2,1,2,2],[3,1,3,2],[4,1,4,2],[5,1,5,2],[6,1,6,2],[7,1,7,2],[8,1,8,2],[9,1,9,2],[10,1,10,2],[11,1,11,2],[12,1,12,2],[13,1,13,2],[14,1,14,2]],"flags":["formulas_cached_only"]}
["周口职业技术学院暑假公寓维修项目汇总表"]
["序号","项   目",null,"预计数量","单  位","预算单价\n（元，\n包工料含税）","询价保证金","备     注"]
[1,"新生房间粉刷（三校区）",null,102720,"平方",10,"5万元","底层处理、刮腻子两边收光，质保期1年。以实际完成工程量为准，验收工期：8月15日"]
[2,"实木床板（三校区）",null,1022,"张",160,"1万元","厚1.8cm以上多层木板 ，90cm*190cm ，以实际完成工程量为准，验收工期：8月10日"]
[3,"外墙瓷砖，加固维修(文昌）",null,1200,"平方",106,"1万元","清除松脱瓷片，固定钢丝网，防水涂料，刷真石漆，质保期3年，以实际完成工程量为准，验收工期：8月10日"]
[4,"公共卫生间维修（开元）",null,32,"间",3000,"2万元","1、蹲便（含更换）、洗手池、小便池、墙缝、地砖（含更换）、地缝防水（砸砖、刷防水涂料做丙纶布防水。2管根（含换管及附件）砸砖、注浆、水不漏封堵、恢复，清除垃圾，全屋闭水实验，质保期3年）。3、洗手池下水道改造（改道下水管入室外窨井）3、男生公寓小便池改造感应冲水器、低水箱）质保期1年,以实际完成工程量为准，验收工期：8月10日"]
[5,"塑钢门（三校区）",null,261,"扇",300,"1万元","0.5cm以上厚塑钢品牌，单层玻璃，质保期1年。以实际完成工程量为准，验收工期：8月15日"]
[6,"地漏补缺（三校区）",null,1520,"个",50,"1万元","质保期1年。以实际完成工程量为准，验收工期：8月12日"]
[7,"内墙粉刷（三校区）",null,3200,"平方",20,"1万元","底层处理、内墙腻子两遍，刷内墙乳胶漆。质保期1年。以实际完成工程量为准，验收工期：8月15日"]
[8,"公寓走廊灯安装（三校区）",null,700,"个",60,"1万元","24瓦LED声光控模组含灯罩、线及其他附件，以实际完成工程量为准，验收工期：8月15日"]
[9,"入户木门安装（三校区）",null,83,"扇",450,"1万元","方木框架，盖免漆板，厚不低于4.5cm。验收工期：8月10日"]
[10,"室内窗纱安装（三校区）",null,354,"平方",80,"1万元","塑钢窗纱，验收工期：8月15日"]
[11,"储物柜柜门、柜鼻维修（三校区）",null,"410／760","个","50／20","5000元","和原柜门、柜鼻一致，以实际完成工程量为准，验收工期：8月15日"]
[12,"路灯维修（三校区）",null,25,"个",660,"5000元","100瓦LED灯头，验收工期：8月15日"]
[13,"公寓护栏维修（开元\\中州)",null,300,"米",50,"3000元","国标2cm×4cm，1.2mm厚镀锌方管，焊接刷防一层锈漆、二层面漆。以实际完成工程量为准，验收工期：8月15日"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}